## Overview
OVERVIEW
Language | Vietnamese
No. | Module | Actual | Duration (days) | Start date | End date |  |  | 2017-03-23 | [8 empty] | 2017-04-01 | [29 empty] | 2017-05-01 | [30 empty] | 2017-06-01
[8 empty] | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
[8 empty] | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6
 | time axis 2017-03-23 to 2017-06-30
1 |  | 0% |  |  | 2017-09-04 | 0 | 2017-09-04
2 |  | 0% |  |  | 2017-09-04 | 0 | 2017-09-04
3 |  | 0% |  |  | 2017-09-04 | 0 | 2017-09-04
4 |  | 0% |  |  | 2017-09-04 | 0 | 2017-09-04
5 |  | 0% |  |  | 2017-09-04 | 0 | 2017-09-04
6 |  | 0% |  |  | 2017-09-04 | 0 | 2017-09-04
7 |  | 0% |  |  |  | 0 | 2017-09-04
8 |  | 0% |  |  |  | 0 | 2017-09-04
9 |  | 0% |  |  |  | 0 | 2017-09-04
10 |  | 0% |  |  |  | 0 | 2017-09-04
11 |  | 0% |  |  |  | 0 | 2017-09-04
12 |  | 0% |  |  |  | 0 | 2017-09-04
13 |  | 0% |  |  |  | 0 | 2017-09-04
14 |  | 0% |  |  |  | 0 | 2017-09-04
15 |  | 0% |  |  |  | 0 | 2017-09-04
16 |  | 0% |  |  |  | 0 | 2017-09-04
17 |  | 0%
18 |  | 0%
19 |  | 0%
20 |  | 0%
21 |  | 0%
22 |  | 0%
23 |  | 0%
24 |  | 0%
25 |  | 0%
26 |  | 0%
27 |  | 0%
28 |  | 0%
29 |  | 0%
30 |  | 0%
31 |  | 0%
32 |  | 0%
33 |  | 0%
34 |  | 0%
35 |  | 0% |  |  |  | 0 | 2017-09-04
|  |  |  | Finish: | 2017-09-04

## Schedule
Project name: | MSTEP UPLOAD | Estimates for MSTEP UPLOAD Function
Project leader | Son-san
Reviewer
Engineer | Thuy-san
Starting date | 2017-06-27
Language | English
No. | Module | Task name | Description | Type | PIC | Days | Start date | End Date | Plan (%) | Actual (%) | Status |  | Note | 2017-06-27 | [8 empty] | 2017-07-06 | [29 empty] | 2017-08-05
[14 empty] | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
[14 empty] | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
[14 empty] | 2017-06-27 | 2017-06-28 | 2017-06-29 | 2017-06-30 | 42917 | 42918 | 42919 | 42920 | 42921 | 42922 | 42923 | 42924 | 42925 | 42926 | 42927 | 42928 | 42929 | 42930 | 42931 | 42932 | 42933 | 42934 | 42935 | 42936 | 42937 | 42938 | 42939 | 42940 | 42941 | 42942 | 42943 | 42944 | 42945 | 42946 | 42947 | 42948 | 42949 | 42950 | 42951 | 42952 | 42953 | 42954 | 42955 | 42956 | 42957 | 42958 | 42959 | 42960 | 42961 | 42962 | 42963 | 42964 | 42965 | 42966 | 42967 | 42968 | 42969 | 42970 | 42971 | 42972 | 42973 | 42974 | 42975 | 42976 | 42977 | 42978 | 42979 | 42980 | 42981 | 42982
|  | Design Home Page layout | - Design layout for Home page - Create layout | New |  | 3 | 2017-08-17 | 2017-08-22 | 100%
|  | Design File/Image Page layout | - Design layout for File Page - Create layout for Image Page | New |  | 1.5 | 2017-08-22 | 2017-08-23 | 100%
|  | Create dropdown | Create dropdown when click right mouse | New |  | 0.5 | 2017-08-23 | 2017-08-24 | 100%
|  | Upload File function | - Create upload file function - Drag & Drop Image/File Function | New |  | 1.5 | 2017-08-24 | 2017-08-25 | 100%
|  | Display file | - Display: List/ table | New |  | 1 | 2017-08-28 | 2017-08-28 | `
|  | Display information of file when clicked file | This block display on left sidebar Information will display: - Name - Modify Date - Folder number - File number | New |  | 0.5 | 2017-08-29 | 2017-08-29 | 100%
|  | Remove Folder/ File | When click Delete Folder/File - B1: Show popup confirm yes/no - B2: If yes, alert deleted success and row contains file/folder deleted. If no, close popup. | New |  | 0.5 | 2017-08-29 | 2017-08-29 | 100%
|  | Create new Folder | When click create folder: - B1: Show popup has: + textbox : name folder + button: create - B2: Alert success - B3: Folder created Process create folder | New |  | 1 | 2017-08-30 | 2017-08-30 | 100%
|  | Edit Folder | When click edit folder: - B1: Show popup has: + textbox: Name current (can edit) + button: Edit - B2: Alert success. - B3: Folder Name edited | New |  | 0.5 | 2017-08-31 | 2017-08-31 | 100%
|  | Responsive | Responsive Home Page, File/ Image layout, popup | New |  | 1 | 2017-09-04 | 2017-09-04 | 100%
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100
100

## Master Data
STATUS LEVEL
Status | Level |  | Task status
Processing | 0 |  | New
Behind | 1 |  | Re-new
Planned | 2 |  | Fix bug
Planning | 3 |  | Edit
Error | 4 |  | Other
Finish | 5
| English | Japanese | Vietnamese
7 | Sa | 土 | T7
1 | Su | 日 | CN
2 | Mo | 月 | T2
3 | Tu | 火 | T3
4 | We | 水 | T4
5 | Th | 木 | T5
6 | Fr | 金 | T6